## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16390 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 04/05/2025 | BHABANI PRASAD MANNA | 77.91 | 0 | 0 | 55
2 | PURBA MEDINIPUR |  | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16390 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000018/2023-2024 | 116/TD | 06/04/2023 | 16/05/2023 | AQUATECH ENGINEERS | 74.22 | 34.96 | 47.11 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16390 | Augmentation | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Habichak Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000305/2023-2024 | 602/TD | 17/05/2023 | 01/07/2023 | SOUMEN KUMAR GHOSH | 25.91 | 25.89 | 99.92 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16390 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 352/TD | 26/04/2023 | 26/04/2023 | Resource Division | 8.83 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16390 | Augmentation | Electric Quotation for HABICHAK Water Supply SchemeT/W-III (Ref. ID-204049767) |  |  | BILL/01633/2023-2024 | BP-2023-24-142 | 27/07/2023 | 27/07/2023 | WBSEDCL | 3.76 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16390 | Augmentation | Electric Quotation for HABICHAK Water Supply SchemeT/W-IV (Ref. ID-204049766) |  |  | BILL/01634/2023-2024 | BP-2023-24-141 | 27/07/2023 | 27/07/2023 | WBSEDCL | 3.4 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16390 | Augmentation | Additional Electric Quotiaton for HABICHAK Water Supply Scheme, T/W- II, (Ref. ID-860281634) |  |  | BILL/02879/2023-2024 | BP-2023-24-322 | 01/11/2023 | 01/11/2023 | WBSEDCL | 2.27 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16390 | Augmentation | Land filling with silver sand and land development of approach road and other side of 2 (Two) nos Boosting T/W site at Habichak W/S scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000375/2024-2025 | 1607/TSD | 28/10/2024 | 17/11/2024 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.82 | 0 | 0 | 100
Total | [13 empty] | 199.11 | 60.86 | 30.56