## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) | SM/16453 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 2096/TD | 29/08/2023 | 29/08/2023 | Resource Division | 26.91 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) | SM/16453 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 2636/TD | 13/10/2023 | 13/10/2023 | Resource Division | 8.14 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) | SM/16453 | Retrofitting | Providing 1321 Nos FHTC (Functional Household Tap Connection) with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Bhagawanpur-II Block under Contai Sub Division of Tamluk Division, PHE DTe.Purba Medinipur (Phase -II) |  | Junior Engineer | ORD/000401/2023-2024 | 1069/TD | 08/06/2023 | 23/07/2023 | TAPAS SANTRA | 91.09 | 0 | 0 | 0
Total | [13 empty] | 126.14 | 0 | 0