## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | SM/16458 | Augmentation | Laying of Distribution pipe line,Rising main pipe line, Pump House, Boundary Wall, with allied works of MANDARMANI & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Phase-III) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 842/TD | 31/05/2023 | 10/07/2023 | DILIP KUMAR GHOSH | 94.7 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | SM/16458 | Augmentation | Pipe crossing for laying Distribution pipe line to provide FHTC (9 nos.) of Mondarmoni W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (NP- 8 - 6, NP- 48 - 50, NP-50 - 52) | Assistant Engineer |  | ORD/000373/2023-2024 | 1010/TD | 05/06/2023 | 25/06/2023 | UNIQUE AGENCY | 7.52 | 7.52 | 100 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | SM/16458 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001999/2022-2023 | 901/W/MMD | 27/03/2023 | 22/11/2026 | S.S.GHORAI | 12.63 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | SM/16458 | Augmentation | Sinking of 250mm. X 150mm dia. X 250 mtr. Deep tube well by direct rotary rig method for 3rd Tubewell at Ramnagar-II Block of Mandarmoni Water Supply Scheme under Digha Sub-Division of Tamluk Division,PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000564/2023-2024 | 2050/TD | 25/08/2023 | 29/09/2024 | PADMA ENGINEERING CO. | 14.21 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | SM/16458 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of MANDARMONI W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004957283/QUOT/03 DT. 20-11-2024 Application NO- 2004957283 Application type-New connection Consumer Id- 204450783 |  |  | BILL/03243/2024-2025 | C122406894909 | 05/12/2024 | 05/12/2024 | WBSEDCL | 3.28 | 0 | 0 | 0
Total | [13 empty] | 132.34 | 7.52 | 5.68