## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) | SM/16460 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (172 nos) under JJM with allied work for Panchrol PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000113/2023-2024 | 243/TD | 19/04/2023 | 05/07/2025 | KRISHNENDU SEKHAR DAS | 61.6 | 28.15 | 45.71 | 50
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) | SM/16460 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) | SM/16460 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001994/2022-2023 | 899/W/MMD | 27/03/2023 | 16/03/2025 | M/S EMMESS | 12.63 | 8.28 | 65.51 | 90
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) | SM/16460 | Augmentation | Quotation For New Service Connections at Tube Well-III of Panchrol W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746343 Consumer ID.-204313789 Application Date.-29/05/2024 |  |  | BILL/01140/2024-2025 | BP-2024-25-251 | 06/06/2024 | 06/06/2024 | WBSEDCL | 4.71 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) | SM/16460 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF DECEMBER'2024 UNDER HESD, PHE DTE |  |  | BILL/04364/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.22 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) | SM/16460 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF DECEMBER'2023 UNDER HESD, PHE DTE |  |  | BILL/04352/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.24 | 0 | 0 | 0
Total | [13 empty] | 81.52 | 36.43 | 44.69