## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) | SM/16462 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (239 nos) under JJM with allied work for Bheribaranga PWSS within Ramnagar -II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000117/2023-2024 | 247/TD | 19/04/2023 | 05/07/2025 | KRISHNENDU SEKHAR DAS | 66.11 | 11.35 | 17.17 | 75
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) | SM/16462 | Augmentation | Quotation for new service connection at tw-III of Bheribaranga ws under MMD,PHE Dte ,Block-Ramnagar-II. Digha CCC Application no-2004764489 CON ID-204324289 |  |  | BILL/01225/2024-2025 | BP-2024-25-290 | 18/06/2024 | 18/06/2024 | WBSEDCL | 4.32 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) | SM/16462 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001990/2022-2023 | 897/W/MMD | 27/03/2023 | 16/03/2025 | A.S.ENTERPRISE | 12.62 | 0 | 0 | 75
Total | [13 empty] | 83.05 | 11.35 | 13.66