## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme | SM/16464 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte.[PART-II] | Assistant Engineer | Junior Engineer | ORD/000454/2022-2023 | .1854/TD | 21/11/2022 | 11/12/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.09 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme | SM/16464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 2094/TD | 29/08/2023 | 29/08/2023 | Resource Division | 15.65 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme | SM/16464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 3006/TD | 29/11/2023 | 29/11/2023 | Resource Division | 10.08 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme | SM/16464 | Augmentation | Sinking of Tubewell, 250 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Soil investigation, Pump House, Boundary wall, Rising Main & Accommodate FHTC (1636 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-II PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000680/2023-2024 | 2709/TD | 30/10/2023 | 27/04/2024 | TAPAS SANTRA | 480.26 | 0 | 0 | 0
Total | [13 empty] | 510.08 | 0 | 0