## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) | SM/16465 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of CHIRULIA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004692025/QUOT/03/97 DT. 25-04-2024 Application NO- 2004692025 Application type-New connection Consumer Id- 204287568 |  |  | BILL/00853/2024-2025 | BP-2024-25-165 | 15/05/2024 | 15/05/2024 | WBSEDCL | 3.24 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) | SM/16465 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) | SM/16465 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (105 nos) under JJM with allied work for CHIRULIA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000299/2023-2024 | 589/TD | 17/05/2023 | 29/05/2025 | SK MAIDUL ISLAM | 53.24 | 13.24 | 24.87 | 30
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) | SM/16465 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Junior Engineer, Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001989/2022-2023 | 896/W/MMD | 27/03/2023 | 19/10/2027 | ECO ENTERPRISE | 12.63 | 8.53 | 67.49 | 85
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) | SM/16465 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF AUGUST'2024 UNDER HESD, PHE DTE |  |  | BILL/04360/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.2 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) | SM/16465 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF SEPT'2024 UNDER HESD, PHE DTE |  |  | BILL/04361/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.24 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) | SM/16465 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF OCTOBER'2023 UNDER HESD, PHE DTE |  |  | BILL/04350/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.17 | 0 | 0 | 0
Total | [13 empty] | 71.84 | 21.77 | 30.3