## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Dulalpur PWSS under Egra-II Block (Phase-II) | SM/16466 | Retrofitting | Schedule for retrofitting to accommodate FHTC under JJM in DULALPUR PWSS within Egra-II Block under DighaSub-Division of Tamluk Division,P HE Dte. in the District of Purba Medinipur (Part-B) | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 246/TD | 19/04/2023 | 09/05/2023 | AYSAN KHAN | 5.16 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Dulalpur PWSS under Egra-II Block (Phase-II) | SM/16466 | Retrofitting | Retrofitting to accommodate FHTC (Phase-II) under JJM in DULALPUR PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur (Part-A) | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 245/TD | 19/04/2023 | 19/05/2023 | AYSAN KHAN | 25.68 | 19.78 | 77.03 | 100
Total | [13 empty] | 30.83 | 19.78 | 64.15