## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (545 NOS) UNDER JJM SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE VII,BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA MEDINIPUR. (PHASE-III) | SM/16468 | Retrofitting | Balance work for retrofitting to accommodate FHTC (545 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-VII Block - Kolaghat in the District of Purba Medinipur.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000120/2023-2024 | 251/TD | 19/04/2023 | 14/05/2023 | MRITYUNJOY PARIA | 32.97 | 30.37 | 92.11 | 100
Total | [13 empty] | 32.97 | 30.37 | 92.11