## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (1180 NOS) AND LAYNE OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XI, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA M | SM/16469 | Retrofitting | Balance work for Retrofitting to accommodate FHTC (990 nos.) and laying of left-out portion UPVC pipeline due to uncovered area at different nodel point under JJM in Surface water based Water Supply Scheme for Zone-XI, Block- Kolaghat in the District of Purba Medinipur. (Phase-III) [PART-A) | Assistant Engineer | Junior Engineer | ORD/000247/2023-2024 | 512/TD | 11/05/2023 | 20/06/2023 | TAPAS SANTRA | 81.84 | 0 | 0 | 85
2 | PURBA MEDINIPUR |  | Tamluk Division | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (1180 NOS) AND LAYNE OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XI, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA M | SM/16469 | Retrofitting | Balance work for Retrofitting to accommodate FHTC (190 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-XI Block - Kolaghat in the District of Purba Medinipur.(Phase-III)[PART-B] | Assistant Engineer | Junior Engineer | ORD/000121/2023-2024 | 252/TD | 19/04/2023 | 09/05/2023 | MISHRA ENTERPRISE | 9.69 | 0 | 0 | 100
Total | [13 empty] | 91.53 | 0 | 0