## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme | SM/16711 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bagmari Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000692/2021-2022 | 1741/TD | 03/02/2022 | 23/02/2022 | HORIZEN | 3.67 | 3.14 | 85.45 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme | SM/16711 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 3008/TD | 29/11/2023 | 29/11/2023 | Resource Division | 5.72 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme | SM/16711 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 2635/TD | 13/10/2023 | 13/10/2023 | Resource Division | 5.72 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme | SM/16711 | Augmentation | Payment of WBSEDCL for Quotation of Shifting of 11 KV line of Bagmari Water Supply Scheme within Egra-II Block |  |  | BILL/01476/2023-2024 | BP-2023-24-664 | 15/12/2023 | 15/12/2023 | WBSEDCL | 4.64 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Bagmari Water Supply Scheme | SM/16711 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bagmari Water Supply Scheme, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001753/2022-2023 | 632/W/MMD | 20/03/2023 | 16/09/2023 | JOYSHREE CONCERN | 13.56 | 0.64 | 4.73 | 90
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme | SM/16711 | Augmentation | Instalation of display Board at different work site of Kanakpur Retrofitting PWSS in Potashpur - I Block, Argoal, Bagmari, Pratapdighi Retrofitting PWSS in Potashpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001188/2023-2024 | 2336/CSD | 29/12/2023 | 13/01/2024 | THE GODFATHER TRADING COMPANY | 0.83 | 0.83 | 100 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme | SM/16711 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 100cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bagmari Water Supply Scheme within Egra-I Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 459/TD | 04/05/2023 | 01/10/2025 | AJIT KUMAR SOM | 241.82 | 161.5 | 66.78 | 70
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bagmari Water Supply Scheme | SM/16711 | Augmentation | Renovation & Repairing of existing pump house H/W site and 2nd TW Site of Bagmari Water Supply Scheme within Egra-I Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000449/2024-2025 | 3616/TD | 27/11/2024 | 25/07/2025 | SOM CONSTRUCTION | 11.36 | 0 | 0 | 0
Total | [13 empty] | 287.33 | 166.11 | 57.81