## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | SM/16713 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000063/2023-2024 | 1222/W/MMD | 25/04/2023 | 22/10/2023 | TAPAN KUMAR SARKAR | 11.76 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | SM/16713 | Augmentation | Laying of Distribution pipe line, Rising main pipe line with allied works of Pratapdighi & its adjoining mouzas Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000531/2023-2024 | 1826/TD | 07/08/2023 | 28/12/2024 | GIRI CONSTRUCTION | 55.97 | 0 | 0 | 45
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | SM/16713 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Pratapdighi Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer |  | ORD/000779/2025-2026 | 3042/TD | 18/12/2025 | 16/02/2026 | MAHARAJ NAYAK | 3.61 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | SM/16713 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 20/01/2025 | B. K. ENTERPRISE | 74.56 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | SM/16713 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of PRATAPDIGHI W/S Scheme under MMD, PHE, Dte. Block- Patashpur-II, wbsedcl office: PATASHPUR C.C.C. Ref. Memo No- 2005628515/QUOT/03/2292 DT.10-02-2026 Application NO- 2005628515 Application type-New connection Reference Id- 204823137 |  |  | BILL/05692/2025-2026 |  | 19/02/2026 | 19/02/2026 | WBSEDCL | 3.2 | 0 | 0 | 0
Total | [13 empty] | 149.11 | 0 | 0