## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16939 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate under JJM with allied work for Dariapur PWSS within Contai-II (Deshpran) Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, PHE Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/000143/2023-2024 | 286/TD | 20/04/2023 | 19/06/2023 | BUNBA CONSTRUCTION | 28.63 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16939 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 343/TD | 26/04/2023 | 26/04/2023 | Resource Division | 4.86 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16939 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Deshopran in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000049/2023-2024 | 1206/W/MMD | 25/04/2023 | 22/10/2023 | BHABANI PRASAD MANNA | 34.45 | 0 | 0 | 53
4 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16939 | Augmentation | Instalation of display Board at different work site of Haipur, Damodarpur Retrofitting PWSS in Contai - I Block, Dariapur & Bankiput Retrofitting PWSS in Contai - II (Deshopran) Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001167/2023-2024 | 2332/CSD | 29/12/2023 | 13/01/2024 | JASODA ENTERPRISE | 0.83 | 0.83 | 99.78 | 100
Total | [13 empty] | 68.77 | 0.83 | 1.2