## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran,Egra-I,Egra-II,Khejuri-I | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16941 | New | Material Requisition To Resource Division |  |  | RTOR000292/2022-2023 | 2910/TD | 21/11/2023 | 21/11/2023 | Resource Division | 10.62 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran,Egra-I,Egra-II,Khejuri-I | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16941 | New | Installation of display Board at 55 nos. different work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000330/2024-2025 | 3289/TD | 05/10/2024 | 25/10/2024 | MISHRA ENTERPRISE | 9.16 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Deshopran,Egra-I,Egra-II,Khejuri-I | Midnapore Mechanical | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16941 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 10/09/2024 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
Total | [13 empty] | 30.2 | 0 | 0