## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Dhanghara PWSS to Accommodate FHTC under JJM with Allied works under Contai-III Block (Phase-II) | SM/16946 | Augmentation | Laying Distribution Pipe Line With allied Works for Augmentation Of Dhanghara Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division,PHE Dte., Purba Medinipur District. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000319/2023-2024 | 665/TD | 19/05/2023 | 18/06/2023 | M/S S. S. ENTERPRISE | 58.98 | 56.28 | 95.42 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Dhanghara PWSS to Accommodate FHTC under JJM with Allied works under Contai-III Block (Phase-II) | SM/16946 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 20/01/2025 | B. K. ENTERPRISE | 74.56 | 0 | 0 | 100
Total | [13 empty] | 133.54 | 56.28 | 42.14