## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16948 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000055/2023-2024 | 1227/W/MMD | 25/04/2023 | 22/10/2023 | SOUMEN ELECTRIC | 12.14 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran | Tamluk Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16948 | New | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000419/2023-2024 | 1100/TD | 08/06/2023 | 01/12/2025 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 0 | 0 | 51
Total | [13 empty] | 258.08 | 0 | 0