## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17194 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 04/05/2025 | BHABANI PRASAD MANNA | 77.91 | 0 | 0 | 55
2 | PURBA MEDINIPUR |  | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17194 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000018/2023-2024 | 116/TD | 06/04/2023 | 16/05/2023 | AQUATECH ENGINEERS | 74.22 | 35.83 | 48.27 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17194 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 348/TD | 26/04/2023 | 26/04/2023 | Resource Division | 8.83 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17194 | Augmentation | Additional quotation for Kulbari w/s scheme PH III in the district of Purba Medinipur under MMD PHE Dte. (App ID 100000118086, Con ID 860311696) |  |  | BILL/02429/2024-2025 | C102415733205 | 05/10/2024 | 05/10/2024 | WBSEDCL | 0.38 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17194 | Augmentation | Quotation bill for new service connection at Kulbari Boosting TW IV Application No.-2004567339, Ref ID.-204195755 |  |  | BILL/03934/2023-2024 | BP-2023-24-725 | 23/02/2024 | 23/02/2024 | WBSEDCL | 11.01 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17194 | Augmentation | Quotation bill for new service connection at Kulbari w/s scheme boosting TW III Application No.-2004567719, Ref.-204195754 |  |  | BILL/03933/2023-2024 | BP-2023-24-724 | 23/02/2024 | 23/02/2024 | WBSEDCL | 10.34 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17194 | Augmentation | Additional quotation for Kulbari w/s scheme PH IV in the district of Purba MEdinipur under MMD PHE Dte. (Ref ID 860321422, App ID 100000126272) |  |  | BILL/03978/2024-2025 | C012552983326 | 31/01/2025 | 31/01/2025 | WBSEDCL | 0.91 | 0 | 0 | 0
Total | [13 empty] | 183.6 | 35.83 | 19.51