## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17221 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 359/TD | 26/04/2023 | 26/04/2023 | Resource Division | 4.41 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17221 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000039/2023-2024 | 1208/W/MMD | 25/04/2023 | 22/10/2023 | BHABANI PRASAD MANNA | 11.44 | 7.08 | 61.89 | 50
3 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/17221 | Augmentation | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000020/2023-2024 | 118/TD | 06/04/2023 | 16/05/2023 | AQUATECH ENGINEER | 61.66 | 15.68 | 25.42 | 100
Total | [13 empty] | 77.52 | 22.76 | 29.36