## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Material Requisition To Resource Division |  |  | RTOR000293/2022-2023 | 2959/TD | 27/02/2023 | 27/02/2023 | Resource Division | 54.95 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Laying distribution System & Accommodate FHTC (1250 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000433/2023-2024 | 1408/TD | 12/07/2023 | 30/09/2023 | UCON | 204.9 | 0 | 0 | 25
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Laying distribution System, Construction of Pump House, Construction of Boundary Wall & Accommodate FHTC (1250 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (Part-C) | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000435/2023-2024 | 1410/TD | 12/07/2023 | 27/06/2025 | NARAYAN CHANDRA DAS | 200.01 | 0 | 0 | 45
4 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Laying distribution System, Construction of Pump House Accommodate FHTC (1100 nos) & Rising Main including interconnection for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000432/2023-2024 | 1407/TD | 12/07/2023 | 30/09/2023 | BARH CONSTRUCTION | 205.81 | 0 | 0 | 50
5 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 133/TD | 05/01/2024 | 05/01/2024 | Resource Division | 27.7 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Quotation Bill for New Service connection at T/W NO-I Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, BHAGWANPUR C.C.C. Ref. Memo No- 2004638854/QUOT/03 DT. 13-03-2024 Application NO- 2004638854 Application type-New connection CONSUMER ID: 204243849 |  |  | BILL/04739/2023-2024 | BP-2023-24-911 | 28/03/2024 | 28/03/2024 | WBSEDCL | 2.77 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Quotation Bill for New Service connection at T/W NO-III Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, BHAGWANPUR C.C.C. Ref. Memo No- 2004638811/QUOT/03 DT. 13-03-2024 Application NO- 2004638811 Application type-New connection CONSUMER ID: 204243848 |  |  | BILL/04748/2023-2024 | BP-2023-24-912 | 28/03/2024 | 28/03/2024 | WBSEDCL | 3.13 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Quotation Bill for New Service connection at T/W NO-II Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004698092/QUOT/03 DT. 23-04-2024 Application NO- 2004698092 Application type-New connection Consumer Id- 204285056 |  |  | BILL/00706/2024-2025 | BP-2024-25-139 | 09/05/2024 | 09/05/2024 | WBSEDCL | 10.71 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Bhagawanpur-I | Central Drilling | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Laying distribution System & Accommodate FHTC (897 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000434/2023-2024 | 1409/TD | 12/07/2023 | 05/09/2025 | SWADHIN KUMAR CHAKRABORTY | 211.86 | 0 | 0 | 40
11 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Soil investigation, R.C.C. Elevated Reservoir of capacity 550cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (Part-F) | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000633/2023-2024 | 2441/TD | 19/09/2023 | 01/03/2025 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 178.22 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | SM/18303 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
Total | [13 empty] | 22442.02 | 0 | 0