## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | GURGRAM & ADJOINING MOUZAS | SM/18311 | New | Sinking of Tube Well ,Construction of Pump House ,400 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2897 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GURGRAM PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000501/2023-2024 | 1689/TD | 26/07/2023 | 12/07/2025 | TARUN KOLEY | 894.96 | 603.82 | 67.47 | 69
2 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | GURGRAM & ADJOINING MOUZAS | SM/18311 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GURGRAM & ADJOINING MOUZAS, Block- Bhagwanpur I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000309/2023-2024 | 1628/W/MMD | 25/07/2023 | 21/01/2024 | ALPHA ENTERPRISE | 23.68 | 23.17 | 97.87 | 80
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | GURGRAM & ADJOINING MOUZAS | SM/18311 | New | Material Requisition To Resource Division |  |  | RTOR000192/2022-2023 | 2381/TD | 16/01/2023 | 16/01/2023 | Resource Division | 75.63 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | GURGRAM & ADJOINING MOUZAS | SM/18311 | New | Gurgram W/S scheme PH-II,(River Side) Application No.-2004523993 Ref.-204157866 |  |  | BILL/03175/2023-2024 | BP-2023-24-475 | 27/12/2023 | 27/12/2023 | WBSEDCL | 9.17 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | GURGRAM & ADJOINING MOUZAS | SM/18311 | New | Gurgram W/S scheme PH-I,(Primary School) Application No.-2004523960 Ref.-204157826 |  |  | BILL/03176/2023-2024 | BP-2023-24-476 | 27/12/2023 | 27/12/2023 | WBSEDCL | 2.91 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | GURGRAM & ADJOINING MOUZAS | SM/18311 | New | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 121/TD | 05/01/2024 | 05/01/2024 | Resource Division | 17.85 | 0 | 0 | 0
Total | [13 empty] | 1024.19 | 626.99 | 61.22