## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I | SM/18766 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000497/2022-2023 | 1933/TD | 28/11/2022 | 18/12/2022 | ASTER CONSULTANCY | 3.46 | 3.37 | 97.56 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I | SM/18766 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 355 Nos) under JJM with allied work for SANKARPUR (Zone-I) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000520/2023-2024 | 1757/TD | 01/08/2023 | 26/01/2026 | SUSIL KUMAR HAZRA | 193.96 | 49.81 | 25.68 | 55
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-I | SM/18766 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-I in Purba Medinipur District,under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000745/2023-2024 | 2289/W/MMD | 29/08/2023 | 30/07/2025 | S.S.GHORAI | 23.52 | 11.31 | 48.11 | 90
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I | SM/18766 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 2074/TD | 28/08/2023 | 28/08/2023 | Resource Division | 13.25 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I | SM/18766 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 3001/TD | 29/11/2023 | 29/11/2023 | Resource Division | 2.99 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I | SM/18766 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-I PWSS at Ramnagar-I Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001045/2023-2024 | 375/TD | 29/01/2024 | 08/02/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-I | SM/18766 | Augmentation | Quotation for new service connection at Zone-1, TW-1 of Shankarpur (Ramnagar)ws scheme under MMD,PHE Dte Ref. Application no.-2004577423, Con ID-204203250 |  |  | BILL/03723/2023-2024 | BP-2023-24-675 | 15/02/2024 | 15/02/2024 | WBSEDCL | 7.83 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I | SM/18766 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-I Of SANKARPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004721008/QUOT/03 DT. 07-05-2024 Application NO- 2004721008 Application type-New connection Consumer Id- 204298882 |  |  | BILL/00442/2024-2025 | BP-2024-25-170 | 10/06/2024 | 10/06/2024 | WBSEDCL | 31.79 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-I | SM/18766 | Augmentation | Laying distribution pipe line due to Re-design, & Accommodate Balance FHTC ( 155 Nos) under JJM with allied work for SANKARPUR (Zone-I) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. (Part Work Order 1/2) | Assistant Engineer |  | ORD/000195/2024-2025 | 315/TD | 22/01/2025 | 21/02/2025 | PRANAB KUMAR DAS | 49.33 | 0 | 0 | 0
Total | [13 empty] | 327.09 | 65.45 | 20.01