## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Purba Medinipur District July 2023 | SM/19093 | Support-IEC | Organize one day Sub Division level orientation programme on JJM involving PRI Functionaries & VWSC members at Purba Medinipur district and conceptualization, design , implementation of community sensitization / mobilization activities using various mediums on JJM, provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water quality issues , water conservation and WASH related issues as per operational guideline of JJM and preparation of web based Digital (A/V) training material (Bengali) at Purba Medinipur District under Tamluk Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000806/2023-2024 | 3284/TD | 20/12/2023 | 20/06/2024 | DEBNATH BROTHERS | 59.2 | 0 | 0 | 58
2 | PURBA MEDINIPUR |  | Tamluk Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Purba Medinipur District July 2023 | SM/19093 | Support-IEC | Organize one day Sub Division level orientation programme on JJM involving PRI Functionaries & VWSC members at Purba Medinipur district and conceptualization, design , implementation of community sensitization / mobilization activities using various mediums on JJM, provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water quality issues , water conservation and WASH related issues as per operational guideline of JJM and preparation of web based Digital (A/V) training material (Bengali) at Purba Medinipur District under Tamluk Division, PHE Dte, , Govt. of West Bengal (PART-B). | Assistant Engineer | Junior Engineer | ORD/001232/2023-2024 | 1043/TD | 15/03/2024 | 15/09/2024 | DEBNATH BROTHERS | 33.97 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Purba Medinipur District July 2023 | SM/19093 | Support-IEC | Wall writing about the benefits of tap water, efficient use of water and water conservation prominent places like Health Center, GP office , BDO Office and other such prominent places for assessment of functionality of Tap water connections under JJM at Purba Medinipur District under Tamluk Division, PHE Dte. Govt of West Bengal | Assistant Engineer |  | ORD/000692/2024-2025 | 2131/TD | 28/06/2024 | 28/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 49.88 | 0 | 0 | 0
Total | [13 empty] | 143.05 | 0 | 0