## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme. | SM/16650 | Augmentation | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001847/2022-2023 | 764/W/MMD | 23/03/2023 | 26/10/2027 | ORIENTAL ENGINEERING CO. | 12.24 | 0 | 0 | 60
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme. | SM/16650 | Augmentation | Supply and installation of Sign Board for depicting the scheme details of different on going Solarization works for the purpose of Geotagging at different PWSS under Khejuri block under Midnapore Mechanical Division, P.H.E. Dte. in the Dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000135/2024-2025 | 648/HESD | 08/07/2024 | 15/07/2024 | THE GODFATHER TRADING COMPANY | 0.35 | 0.3 | 85.54 | 100
Total | [13 empty] | 12.59 | 0.3 | 2.38