## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme. | SM/16655 | Augmentation | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001849/2022-2023 | 766/W/MMD | 23/03/2023 | 19/09/2023 | MENAKA ENTERPRISE | 12.24 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme. | SM/16655 | Augmentation | Electric Quotation for MAHISHADAL BETKUNDU Water Supply Scheme T/W-, (Ref. ID-222016853) |  |  | BILL/02680/2023-2024 | BP-2023-24-268 | 10/10/2023 | 10/10/2023 | WBSEDCL | 0.01 | 0 | 0 | 0
Total | [13 empty] | 12.24 | 0 | 0