## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme. | SM/16666 | Augmentation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000273/2024-2025 | 739/HESD | 01/08/2024 | 16/08/2024 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 2.17 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme. | SM/16666 | Augmentation | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001846/2022-2023 | 763/W/MMD | 23/03/2023 | 10/03/2025 | UNITED TRADERS | 12.24 | 7.15 | 58.39 | 45
Total | [13 empty] | 20.34 | 7.32 | 36