## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Thenkuachak, Zone-II PWSS in the District of Purba Medinipur under JJM programme. | SM/16669 | Augmentation | Rejuvenation of Electro-Mechanical components of Thenkuachak, Zone-II PWSS in the District of Purba Medinipur under JJM programme | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000075/2023-2024 | 1244/W/MMD | 28/04/2023 | 31/03/2025 | TAPAN KUMAR SARKAR | 11.15 | 0 | 0 | 80
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Thenkuachak, Zone-II PWSS in the District of Purba Medinipur under JJM programme. | SM/16669 | Augmentation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at JALPAI and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000064/2024-2025 | 534/HESD | 10/06/2024 | 25/06/2024 | MUKHERJEE ART CENTRE | 2.11 | 0.26 | 12.52 | 75
Total | [13 empty] | 13.27 | 0.26 | 1.99