## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme. | SM/16671 | Augmentation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000268/2024-2025 | 738/HESD | 01/08/2024 | 16/08/2024 | THE GODFATHER TRADING COMPANY | 6.87 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme. | SM/16671 | Augmentation | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001840/2022-2023 | 756/W/MMD | 23/03/2023 | 12/03/2025 | UNITED TRADERS | 11.34 | 0 | 0 | 100
Total | [13 empty] | 18.21 | 0 | 0