## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000096/2023-2024 | 1308/W/MMD | 15/05/2023 | 13/08/2023 | SONSOLITE INFRA AND POWER SOLUTION PVT. LTD. | 133.28 | 107.72 | 80.82 | 80
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000273/2024-2025 | 739/HESD | 01/08/2024 | 16/08/2024 | THE GODFATHER TRADING COMPANY | 8.1 | 1.76 | 21.74 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at BARANALGERIA and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000063/2024-2025 | 532/HESD | 10/06/2024 | 25/06/2024 | THE GODFATHER TRADING COMPANY | 5.28 | 1.76 | 33.33 | 50
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10.05 KWp at T/W NO-I, ZONE- I OF BARANALGERIA W/S SCHEME under MMD,PHE,Dte. BLOCK- EGRA-II WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C Ref. Memo No- 2004765495/APP_RECT/01 DT. 06-06-2024 APPLICATION NO: 2004765495 Consumer Id- 203193703 |  |  | BILL/01722/2024-2025 | BP-2024-25-530 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Net-Metering Solar Power Plant quotation at Deriachak water supply scheme Zone-V, Tube Well-I Matangini CCC Block-Panskura-II Application No.-2004795860 Consumer ID.-202743884 Quotation Date.-26/06/2024 |  |  | BILL/01454/2024-2025 | BP-2024-25-532 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10 KWp at T/W NO-I OF UTTAR KHASDA W/S SCHEME under MMD,PHE,Dte. BLOCK- CONTAI-I WBSEDCL SUPPLY OFFICE: CONTAI C.C.C Ref. Memo No- 2004790808/APP_RECT/01 DT. 24-06-2024 APPLICATION NO: 2004790808 Consumer Id- 201090792 |  |  | BILL/01470/2024-2025 | BP-2024-25-531 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10 KWp at T/W NO-I OF ALADARPUT W/S SCHEME under MMD,PHE,Dte. BLOCK- CONTAI-II WBSEDCL SUPPLY OFFICE: CONTAI C.C.C Ref. Memo No- 2004884469/APP_RECT/01 DT. 03-09-2024 APPLICATION NO: 2004884469 Consumer Id- 200883228 |  |  | BILL/02991/2024-2025 |  | 06/11/2024 | 06/11/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10.05 KWp at T/W NO-I OF BATHUARI W/S SCHEME under MMD,PHE,Dte. BLOCK- EGRA-II WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C Ref. Memo No- 2004765511/APP_RECT/01 DT. 06-06-2024 APPLICATION NO: 2004765511 Consumer Id- 200643580 |  |  | BILL/01452/2024-2025 | BP-2024-25-534 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Application for SOLAR POWER PLANT Of 10.05 KWp at T/W NO-I, ZONE- II OF BARANALGERIA W/S SCHEME under MMD,PHE,Dte. BLOCK- EGRA-II WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C Ref. Memo No- 2004765528/APP_RECT/01 DT. 06-06-2024 APPLICATION NO: 2004765528 Consumer Id- 203543000 |  |  | BILL/01451/2024-2025 | BP-2024-25-533 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10.05 KWp at T/W NO-I OF DULALPUR W/S SCHEME under MMD,PHE,Dte. BLOCK- EGRA-II WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C Ref. Memo No- 2004765507/APP_RECT/01 DT. 06-06-2024 APPLICATION NO: 2004765507 Consumer Id- 202969561 |  |  | BILL/01453/2024-2025 | BP-2024-25-535 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR Quotation Bill for T/W NO-I Of BHERI BARANGA W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Application NO- 2005045684 Application type-SOLAR connection BILLING TYPE- NET BILLING Consumer Id- 202930285 |  |  | BILL/04387/2024-2025 | C032566208362 | 21/03/2025 | 21/03/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR Quotation Bill for T/W NO-I Of PALDHUI W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Application NO- 2005045677 Application type-SOLAR connection BILLING TYPE- NET BILLING Consumer Id- 202930302 |  |  | BILL/04388/2024-2025 | C032566143440 | 21/03/2025 | 21/03/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | QUOTATION FOR SOLAR INSTALLATION AT KALINDI PUMP HOUSE NO-I. CON ID-223006481 APPLICATION NO.-2004857974 CCC-PICHABONI CCC |  |  | BILL/02465/2025-2026 |  | 02/09/2025 | 02/09/2025 | WBSEDCL | 0.6 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR Quotation Bill for T/W NO-I Of ALADARPUT W/S Scheme under MMD, PHE, Dte. Block- Contai-II, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Application NO- 2005119327 Application type-SOLAR connection Consumer Id- 200883228 |  |  | BILL/04974/2024-2025 |  | 20/03/2025 | 20/03/2025 | WBSEDCL | 0.31 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR Quotation Bill for T/W NO-I Of BATHUARI W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Application NO- 2004765511 DT. 02/04/2025 REF.NO- M-06 DT. 2/4/2025 Application type-SOLAR connection Consumer Id- 200643580 |  |  | BILL/00715/2025-2026 |  | 08/05/2025 | 08/05/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR Quotation Bill for T/W NO-I Of BARANALGERIA, ZONE-I W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Application NO- 2004765495 DT. 02/04/2025 REF.NO- M-04 DT. 2/4/2025 Application type-SOLAR connection Consumer Id- 203193703 |  |  | BILL/00714/2025-2026 | W/267/25-26 | 07/08/2025 | 07/08/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | Application fees for SOLAR POWER PLANT Of 10.05 KWp at T/W NO-I, ZONE-I OF AMARSIKASBA W/S SCHEME under MMD,PHE,Dte. BLOCK- PATASHPUR-I WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C Ref. Memo No- 2005064066/APP_RECT/01 DT. 29-01-2025 APPLICATION NO: 2005064066 Consumer Id-223049745 |  |  | BILL/04502/2024-2025 | C032587427140 | 27/03/2025 | 27/03/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR Quotation Bill for T/W NO-I Of UTTAR KHASDA W/S Scheme under MMD, PHE, Dte. Block- Contai-II, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Application NO- 2005119364 Application type-SOLAR connection Consumer Id- 201090792 |  |  | BILL/04975/2024-2025 |  | 20/03/2025 | 20/03/2025 | WBSEDCL | 0.31 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR Quotation Bill for T/W NO-I Of DULALPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Application NO- 2004765507 DT. 02/04/2025 REF.NO- M-05 DT. 2/4/2025 Application type-SOLAR connection Consumer Id- 202969561 |  |  | BILL/00716/2025-2026 |  | 08/05/2025 | 08/05/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR Quotation Bill for T/W NO-I Of BARANALGERIA, ZONE-II W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Application NO- 2004765528 REF NO- M-07 DT.2/4/25 Application type-SOLAR connection Consumer Id- 203543000 |  |  | BILL/00713/2025-2026 |  | 08/05/2025 | 08/05/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR Quotation Bill for T/W NO-I, ZONE-I Of AMARSIKASBA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Application NO- 2005064066 DT.21/02/2025 Application type-SOLAR connection Consumer Id- 223049745 |  |  | BILL/04464/2024-2025 | C032566139941 | 21/03/2025 | 21/03/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
22 | PURBA MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16929 | Solarisation | SOLAR QUOTATION BILL FOR KHEJURI W/S SCHEME ZONE-I, T/W NO-I UNDER MMD,PHE DTE. WBSEDCL CCC: KHEJURI C.C.C. APL.ID: 2005124313 CON.ID: 223167141 DT. 5/6/2026 |  |  | BILL/01202/2026-2027 |  | 29/06/2026 | 29/06/2026 | WBSEDCL | 0.12 | 0 | 0 | 0
Total | [13 empty] | 149.61 | 111.24 | 74.35