## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17296 |  | Solarization of grid connected pumping installation at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001821/2022-2023 | 730/W/MMD | 23/03/2023 | 19/09/2023 | MEGA SOLAR ENERGY | 6.26 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17296 |  | Quotation Bill for new service connection at TW-III of Barsundra w/s scheme,under MMD,PHE,Dte.,Purba Medinipur Block-Haldia, C.C.C.-Brajalalchak Application no.-2004651015 Application Type-New connection Quotation Date-22/03/2024 Quotation Due Date-24/03/2025 Contract Demand-10209 W |  |  | BILL/00018/2024-2025 | BP-2024-25-17 | 08/04/2024 |  | WBSEDCL | 4.22 | 0 | 0 | null
Total | [13 empty] | 10.48 | 0 | 0