## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17305 | Solarisation | Solarization of grid connected pumping installation at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001818/2022-2023 | 729/W/MMD | 23/03/2023 | 19/09/2023 | MEGA SOLAR ENERGY | 6.26 | 4.66 | 74.47 | 50
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17305 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at BARBASUDEBPUR and adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000065/2024-2025 | 535/HESD | 10/06/2024 | 25/06/2024 | KOLEY ENTERPRISE | 1.23 | 0.18 | 14.43 | 75
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17305 | Solarisation | Quotation Bill for NET METERING at TW-I of Barbasudebpur w/s scheme in the Dist. of Purba Medinipur under MMD PHE Dte. Name of Block-Haldia Name of C.C.C.-Brajalalchak Application no.-2005103166 Consumer ID-224044051 Contractual load-15kw Installed capacity of solar plant-10 kw Quotation Date-20/03/2025 |  |  | BILL/00718/2025-2026 | 42156 | 07/08/2025 | 07/08/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
Total | [13 empty] | 7.72 | 4.84 | 62.73