## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Bajkul, Zone-I, Zone-II & Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17359 | Solarisation | Solarization of grid connected pumping installation at Bajkul, Zone-I, Zone-II and Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001863/2022-2023 | 754/W/MMD | 23/03/2023 | 19/09/2023 | JYOTY SOLAR POWER | 18.78 | 4.85 | 25.83 | 60
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Bajkul, Zone-I, Zone-II & Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17359 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at ARJUNNAGAR and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000062/2024-2025 | 529/HESD | 10/06/2024 | 25/06/2024 | M/S. S.R. ENTERPRISE | 1.41 | 0.53 | 37.5 | 70
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Bajkul, Zone-I, Zone-II & Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17359 | Solarisation | SOLAR Quotation Bill for T/W NO-I, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: KHEJURI C.C.C. Application NO- 2005135252 BILLING TYPE: NET METERING Application type-SOLAR connection Consumer Id- 223040597 |  |  | BILL/03050/2025-2026 |  | 14/11/2025 | 14/11/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
Total | [13 empty] | 20.41 | 5.38 | 26.35