## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17386 | Solarisation | Solarization of grid connected pumping installation at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001875/2022-2023 | 742/W/MMD | 23/03/2023 | 27/02/2025 | PRANAB KUMAR DAS | 6.26 | 4.85 | 77.48 | 80
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17386 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000268/2024-2025 | 738/HESD | 01/08/2024 | 16/08/2024 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 2.56 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17386 | Solarisation | SOLAR Quotation Bill for T/W NO-I Of CHANDANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Application NO- 2005133637 Application type-SOLAR connection Consumer Id- 200685807 |  |  | BILL/00397/2025-2026 | 42156 | 07/08/2025 | 07/08/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
Total | [13 empty] | 13.35 | 5.02 | 37.64