## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17388 | Solarisation | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001877/2022-2023 | 744/W/MMD | 23/03/2023 | 19/09/2023 | M/S. JIT ENTERPRISE | 6.26 | 4.88 | 78.03 | 60
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17388 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different on going Solarisation/ Rejuvenation / Other JJM works for the purpose of Geotagging at BEGUNBERIA & adjacent pwss under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000066/2024-2025 | 525/HESD | 10/06/2024 | 17/06/2024 | S.B.ENTERPRISE | 0.7 | 0.18 | 25.23 | 40
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17388 | Solarisation | Quotation bill for application fees for NET BILLING for solar power plant of 10KWp at Asadtaliya w/s scheme,Block-sutahata in the Dist. of Purba Medinipur under MMD,PHE,Dte. Name of C.C.C.-Chaitanyapur Application no-2004837084 Consumer ID-224044050 Quotation Date-25/07/2024 Quotation Due Date-90days from the date of issue |  |  | BILL/01865/2024-2025 | C082409418031 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17388 | Solarisation | Quotation bill for net metering at TW-I of Asadtaliya w/s scheme in the Dist. of Purba Medinipur under MMD PHE Dte. Name of C.C.C-Chaitanyapur Application No.-2005134001 Consumer ID-224044050 Contractual load-15KW Installed capacity of solar plant-10 KW Quotation Date-24/04/2025 |  |  | BILL/00707/2025-2026 | 42156 | 07/08/2025 | 07/08/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
Total | [13 empty] | 7.12 | 5.06 | 71.11