## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17648 | Solarisation | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002147/2022-2023 | 1050/W/MMD | 29/03/2023 | 25/09/2023 | JYOTY SOLAR POWER | 80.98 | 57.23 | 70.68 | 60
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17648 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation works for the purpose of Geotagging at NANDIGRAM-II and KOLAGHAT Block adjacent PWSS under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000060/2024-2025 | 527/HESD | 10/06/2024 | 25/06/2024 | S.B.ENTERPRISE | 2.29 | 2.11 | 92.19 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17648 | Solarisation | Solar Application Bill for Kolaghat Zone-XIII (Siddha-II) Panskura CCC Application No=2005055788 Consumer ID=202618252 |  |  | BILL/04254/2024-2025 | BP-2024-25-1039 | 26/03/2025 | 26/03/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17648 | Solarisation | Solar Application Bill for Gobindanagar Zone-II,T/W-I Panskura CCC Application No=2005052114 Consumer ID=222250381 |  |  | BILL/04248/2024-2025 | BP-2024-25-1039 | 26/03/2025 | 26/03/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17648 | Solarisation | Quotation bill for Net Billing Kolaghat Zone-V Matangini CCC Application No=2004795860 Consumer ID=202743884 |  |  | BILL/04115/2024-2025 | C022539995216 | 18/02/2025 | 18/02/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17648 | Solarisation | Solar Application Bill for Kolaghat Zone-XII (Siddha-I) Panskura CCC Application No=2005055811 Consumer ID=202618249 |  |  | BILL/04249/2024-2025 | BP-2024-25-1039 | 26/03/2025 | 26/03/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17648 | Solarisation | Solar Application Bill for Kolaghat Zone-IV Panskura CCC Application No=2005052094 Consumer ID=202618255 |  |  | BILL/04250/2024-2025 | BP-2024-25-1039 | 26/03/2025 | 26/03/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
Total | [13 empty] | 83.51 | 59.34 | 71.06