## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17720 | Solarisation | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002064/2022-2023 | 999/W/MMD | 29/03/2023 | 25/09/2023 | THE BUSINESS ENGINEERING INDIA | 6.26 | 4.88 | 78.03 | 60
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17720 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation works for the purpose of Geotagging at different PWSS under CHANDIPUR, MAHISHADAL and KHEJURI Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000182/2024-2025 | 725/HESD | 30/07/2024 | 14/08/2024 | SOUMEN ELECTRIC | 3.7 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17720 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different on going Solarization works for the purpose of Geotagging at different PWSS under Khejuri block under Midnapore Mechanical Division, P.H.E. Dte. in the Dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000135/2024-2025 | 648/HESD | 08/07/2024 | 15/07/2024 | THE GODFATHER TRADING COMPANY | 0.35 | 0.05 | 14.46 | 100
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17720 | Solarisation | Processing fees for solar metering application for Rashikachak w/s scheme in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004647940, C ID 224068591) |  |  | BILL/04733/2023-2024 | BP-2023-24-922 | 28/03/2024 | 28/03/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
Total | [13 empty] | 10.31 | 4.94 | 47.86