## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Gholpukuria, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17722 | Solarisation | Solarization of grid connected pumping installation at Gholpukuria, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002144/2022-2023 | 1047/W/MMD | 29/03/2023 | 25/09/2023 | S.S.GHORAI | 12.51 | 4.85 | 38.74 | 50
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Gholpukuria, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17722 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation works for the purpose of Geotagging at NANDIGRAM-II and KOLAGHAT Block adjacent PWSS under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000060/2024-2025 | 527/HESD | 10/06/2024 | 25/06/2024 | S.B.ENTERPRISE | 2.29 | 0.18 | 7.68 | 100
Total | [13 empty] | 14.8 | 5.02 | 33.94