## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at KANKTYA PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17756 | Solarisation | Solarization of grid connected pumping installation at KANKTYA PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002135/2022-2023 | 1038/W/MMD | 29/03/2023 | 25/09/2023 | SOUMEN ELECTRIC | 6.26 | 4.89 | 78.03 | 30
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at KANKTYA PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17756 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation works for the purpose of Geotagging at SAHID MATANGINI, TAMLUK and PANSKURA Block adjacent PWSS under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000055/2024-2025 | 528/HESD | 10/06/2024 | 25/06/2024 | M/S. S.R. ENTERPRISE | 3.52 | 0.18 | 5 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at KANKTYA PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17756 | Solarisation | Solar Application Bill For Kanktia T/W-I Matangini CCC Application No=2004953534 Consumer ID=222079835 |  |  | BILL/03281/2024-2025 | C122407523359 | 06/12/2024 | 06/12/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
Total | [13 empty] | 9.79 | 5.06 | 51.71