## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17761 | Solarisation | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002091/2022-2023 | 1010/W/MMD | 29/03/2023 | 25/09/2023 | MEGA SOLAR ENERGY | 6.26 | 4.66 | 74.47 | 50
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17761 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at BARBASUDEBPUR and adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000065/2024-2025 | 535/HESD | 10/06/2024 | 25/06/2024 | KOLEY ENTERPRISE | 1.23 | 0.18 | 14.43 | 75
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17761 | Solarisation | Quotation bill for application fees for NET BILLING for solar power plant of 10KWp at Dwariberia w/s scheme,Block-sutahata in the Dist. of Purba Medinipur under MMD,PHE,Dte. Name of C.C.C.-Chaitanyapur Application no-2004837078 Consumer ID-224041892 Quotation Date-25/07/2024 Quotation Due Date-90days from the date of issue |  |  | BILL/01864/2024-2025 | BP-2024-25-550 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17761 | Solarisation | Quotation Bill for Application Fee for NET METERING at Dwariberia w/s scheme Block-Haldia under MMD,PHE Dte. Name of CCC-Chaitanyapur Application number -2005183908 Consumer ID-224041892 Quotation Issuance Date-22/04/2025 Quotation valid for 90days from the date of issue |  |  | BILL/00711/2025-2026 |  | 08/05/2025 | 08/05/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17761 | Solarisation | Quotation bill for Net Meter for solar plant at TW-I of Dwariberia w/s scheme, Block-Haldia, in the Dist. of Purba Medinipur under MMD,PHE Dte. Name of C.C.C-Chaitanyapur Application No.-2005541253 Con. ID-224041892 Contractual load-11.19 KW Installed capacity of solar plant-10.3 kWP Quotation Date -01/12/2025 |  |  | BILL/03858/2025-2026 |  | 16/12/2025 | 16/12/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
Total | [13 empty] | 7.65 | 4.84 | 63.24