## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Manikpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17771 | Solarisation | Solarization of grid connected pumping installation at Manikpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002104/2022-2023 | 1025/W/MMD | 29/03/2023 | 25/09/2023 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Manikpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17771 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different on going Solarisation/ Rejuvenation / Other JJM works for the purpose of Geotagging at MANIKPUR & adjacent pwss under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000067/2024-2025 | 526/HESD | 10/06/2024 | 17/06/2024 | S.B.ENTERPRISE | 0.88 | 0 | 0 | 40
Total | [13 empty] | 7.14 | 0 | 0