## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17772 | Solarisation | Solarization of grid connected pumping installation at Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002102/2022-2023 | 1023/W/MMD | 29/03/2023 | 25/09/2023 | SUBHASIS ROY | 6.26 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17772 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at JALPAI and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000064/2024-2025 | 534/HESD | 10/06/2024 | 25/06/2024 | MUKHERJEE ART CENTRE | 2.11 | 0.19 | 8.9 | 75
Total | [13 empty] | 8.37 | 0.19 | 2.24