## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Durmut PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17789 | Solarisation | Solarization of grid connected pumping installation at Durmut PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002080/2022-2023 | 1004/W/MMD | 29/03/2023 | 25/09/2023 | AMITAVA CHAKRABORTY | 6.26 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Durmut PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17789 | Solarisation | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at BARCHUNFALI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000184/2024-2025 | 728/HESD | 30/07/2024 | 14/08/2024 | M/S. S.R. ENTERPRISE | 2.99 | 0.18 | 5.88 | 100
Total | [13 empty] | 9.25 | 0.18 | 1.9