## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Natshallakhya, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17803 |  | Solarization of grid connected pumping installation at Natshallakhya, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002099/2022-2023 | 1015/W/MMD | 29/03/2023 | 25/09/2023 | MEGA SOLAR ENERGY | 6.26 | 0 | 0 | 60
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Natshallakhya, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17803 |  | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation works for the purpose of Geotagging at different PWSS under CHANDIPUR, MAHISHADAL and KHEJURI Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000182/2024-2025 | 725/HESD | 30/07/2024 | 14/08/2024 | SOUMEN ELECTRIC | 3.7 | 0 | 0 | 100
Total | [13 empty] | 9.96 | 0 | 0