## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Uttardalhara Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17809 | Solarisation | Solarization of grid connected pumping installation at Uttardalhara Zone-I and Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002146/2022-2023 | 1049/W/MMD | 29/03/2023 | 25/09/2023 | A-NIK & CO. | 12.52 | 0 | 0 | 40
Total | [13 empty] | 12.52 | 0 | 0