## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Muradpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17874 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Design development works for the purpose of Geotagging at different PWSS under KHEJURI, MAHISHADAL, CHANDIPUR Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000185/2024-2025 | 727/HESD | 30/07/2024 | 14/08/2024 | SOUMEN ELECTRIC | 3.34 | 0 | 0 | 100
Total | [13 empty] | 3.34 | 0 | 0