## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mahammadpur (Bhagabanpur-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17915 | IOT | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at MAHAMMADPUR and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000133/2024-2025 | 649/HESD | 08/07/2024 | 23/07/2024 | SOUMEN ELECTRIC | 1.94 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Mahammadpur (Bhagabanpur-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17915 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Junior Engineer, Haldia Electrical Sub-Division,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division.,Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sourav Mondal, JE/Midnapur Mechanical Sub-Division-,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000551/2025-2026 | 2068/W/MMD | 03/12/2025 | 05/10/2026 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 30
Total | [13 empty] | 3944.87 | 0 | 0