## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | New | -"Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Bhutnirghat ,Choto salkumar, Dalimpur etc under Falakata block in the dist. of Alipurduar under NMD-II P.H E Dte¿ |  |  | ORD/000614/2021-2022 | 1114/NMD-II | 20/09/2021 | 20/10/2021 | M/S PARITOSH BHOWMICK & CO. | 2.15 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under DALIMPUR W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000316/2021-2022 | 625/NMD-II | 06/07/2021 | 06/07/2022 | M/S PARITOSH BHOWMICK & CO. | 4.88 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | New | Operation and Guarding of Pumping machinery at Pump House No. I (AUG.) , Under KALCHINI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000317/2021-2022 | 626/NMD-II | 06/07/2021 | 06/07/2022 | S.P ENTERPRISE (SLG) | 4.88 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under DALIMPUR W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000384/2021-2022 | 551/NMD-II | 06/07/2021 | 06/07/2022 | M/S PARITOSH BHOWMICK & CO. | 4.88 | 0 | 0 | 0
Total | [13 empty] | 16.8 | 0 | 0