## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | New | Supply, delivery of Standby Submersible pumping Machinery for Putimari W/S/S,TW-II under NMD-II,PHE Dte, Dist-Alipurduar. |  |  | ORD/000829/2020-2021 | .816/AMSD | 14/01/2021 | 24/01/2021 | THE BANERJEE CONCERN | 0.5 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂]granuels at different W/S Scheme at Dinhata I Block under CMSD, PHE, Dte. in the dist. Cooch Behar.¿ |  |  | ORD/000003/2021-2022 | 221/CMSD | 24/05/2021 | 08/06/2021 | MUSTAFI CONCERN | 0.96 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under PUTIMARI W/S Scheme, in the dist. Of Cooch Behar. |  |  | ORD/000555/2021-2022 | 595/NMD-II | 06/07/2021 | 06/07/2022 | THE BANERJEE CONCERN | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | New | Operation and Guarding of Pumping machinery at Pump House No. I under PITIMARI W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000499/2021-2022 | 632/NMD-II | 06/07/2021 | 06/07/2022 | M/S P.P ELECTRICALS | 4.88 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | New | Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Satkura, Baro Atabari Pratham Khanda etc under Dinhata Sub Division in the dist. of Cooch Behar under NMD-II P.H.E Dte.¿ |  |  | ORD/000600/2021-2022 | 1119/NMD-II | 20/09/2021 | 20/10/2021 | MADHAB SAHA | 3.29 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under PUTIMARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000386/2021-2022 | 553/NMD-II | 06/07/2021 | 06/07/2022 | M/S P.P ELECTRICALS | 4.88 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under PUTIMARI W/S Scheme, in the dist. Of Cooch Behar. |  |  | ORD/000637/2021-2022 | 665/NMD-II | 06/07/2021 | 06/07/2022 | RAJEEV RANJAN OJHA | 2.97 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | New | Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Satkura,Baro Atabari Pratham Khanda etc under Dinhata Sub Division in the dist. of Cooch Behar¿ |  |  | ORD/000697/2021-2022 | 1310/NMD-II | 03/12/2021 | 18/12/2021 | TAPAN BISWAS | 4.72 | 0 | 0 | 0
Total | [13 empty] | 25.17 | 0 | 0