## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI WATER SUPPLY SCHEME | SM/00026 | New | Operation and Guarding of Pumping machinery at Pump House No. III , Under KALCHINI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000388/2021-2022 | 555/NMD-II | 06/07/2021 | 06/07/2022 | S.P ENTERPRISE (SLG) | 4.88 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI WATER SUPPLY SCHEME | SM/00026 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kalchini block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000518/2021-2022 | 1071/NMD-II | 10/09/2021 | 30/09/2021 | R.K ENTERPRISE | 1.85 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI WATER SUPPLY SCHEME | SM/00026 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. H/W Site under KALCHINI W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000007/2021-2022 | 65/AMSD | 27/04/2021 | 27/07/2021 | M/S CHANDRANATH MUKHERJEE | 1.19 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI WATER SUPPLY SCHEME | SM/00026 | New | Operation and Guarding of Pumping machinery at Pump House No. II, Under KALCHINI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000304/2021-2022 | 613/NMD-II | 06/07/2021 | 06/07/2022 | S.P ENTERPRISE (SLG) | 4.88 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI WATER SUPPLY SCHEME | SM/00026 | New | Operation and Guarding of Pumping machinery at Pump House No. I (H/W SITE) , Under KALCHINI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000392/2021-2022 | 559/NMD-II | 06/07/2021 | 06/07/2022 | M/S CHANDRANATH MUKHERJEE | 4.88 | 0 | 0 | 0
Total | [13 empty] | 17.69 | 0 | 0