## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | New | Making internal wiring and fitting fixing outdoor Luminaries with proper earthing arrangement at P.H No. I of KAIJALIBASTI w/s scheme under NMD-II , PHE, Dte. Alipuduar . |  |  | ORD/000540/2020-2021 | 616/AMSD | 02/11/2020 | 17/11/2020 | S.D CONCERN WORKSHOP | 0.5 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | New | Making internal wiring and fitting fixing outdoor Luminaries with proper earthing arrangement at P.H No. II of KAIJALI BASTY w/s scheme under NMD-II , PHE, Dte. Alipuduar . |  |  | ORD/000539/2020-2021 | 617/AMSD | 02/11/2020 | 17/11/2020 | S.D CONCERN WORKSHOP | 0.5 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at different PWSS under Kumargram Block in the District of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000533/2020-2021 | 1317/NMD-II | 29/12/2020 | 18/01/2021 | SARKAR ELECTRIC | 1.79 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. I under KAIJALI BASTY W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000006/2021-2022 | 64/AMSD | 27/04/2021 | 26/07/2021 | B.B CONCERNED | 1.19 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | New | Operation and Guarding of Pumping machinery at Pump House No. II under KAIJALI BASTY W/S Scheme. In the dist. Of ALIPURDUAR. |  |  | ORD/000502/2021-2022 | 635/NMD-II | 06/07/2021 | 06/07/2022 | BLUE PINE | 4.88 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kumargram block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000520/2021-2022 | 1076/NMD-II | 10/09/2021 | 30/09/2021 | M/S P.P ELECTRICALS | 3.58 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under KAIJALI BASTY W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000308/2021-2022 | 617/NMD-II | 06/07/2021 | 06/07/2022 | B.B CONCERNED | 4.88 | 0 | 0 | 0
Total | [13 empty] | 17.33 | 0 | 0