## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | Operation and Guarding of Pumping machinery at Pump House No. II under BIRPARA (MADARIHAT BLOCK) W/S Scheme. In the dist. Of ALIPURDUAR. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000503/2021-2022 | 636/NMD-II | 06/07/2021 | 06/07/2022 | M/S SAJAHAN CHOWDHURY | 4.88 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | Yard lighting arrangement at Pump House No. I(Head Works site) PHE office Campus under Birpara Water Supply Scheme (Birpara-Madarihat Block) Under Northern Mechanical Division-II P.H.E Dte. |  |  | ORD/000021/2020-2021 | 1075/NMD-II | 16/09/2020 | 16/10/2020 | ALPHA ENTERPRISE | 4.79 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | Renovation of the electrical installation of BIRPARA ( MADARIHAT BLOCK ) W/S scheme T/W No.- II under NMD-II , PHE, Dte. Alipuduar . |  |  | ORD/000538/2020-2021 | 614/AMSD | 02/11/2020 | 17/11/2020 | S.D CONCERN WORKSHOP | 0.53 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | Supply & delivery of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at Dekhlapara T.G P/H No.-I , Birpara p/H No.I, Paschim Khairbari P/H No.II ,Gargenda P/h No.II, Dhumchipara P/HNo.I in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000522/2021-2022 | 1070/NMD-II | 10/09/2021 | 30/09/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.76 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I of Shishubari ,BaraHauda , Madhu T.G W/S schemeand P/H No.II of Birpara Madarihat Block in the district of Alipurduar. |  |  | ORD/000546/2021-2022 | 1018/NMD-II | 27/08/2021 | 16/09/2021 | TAPAN BISWAS | 3.5 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under BIRPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000335/2021-2022 | 702/NMD-II | 08/07/2021 | 08/07/2022 | M/S BHOWMIK & CO. | 2.97 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under BIRPARA (MADARIHAT BLOCK) W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000532/2021-2022 | 639/NMD-II | 06/07/2021 | 06/07/2022 | M/S BHOWMIK & CO. | 4.88 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under BIRPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000379/2021-2022 | 739/NMD-II | 08/07/2021 | 08/07/2022 | GEETA CONSTRUCTION | 2.97 | 0 | 0 | 0
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BIRPARA WATR SUPPLY SCHEME | SM/00035 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
Total | [13 empty] | 36.59 | 0 | 0